## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, you will also update your Atrack Excel file which contains the attendance records for this week. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Electrical
Team Leader Name | James Talbert
Week Number | 2
Attendance Records
Number of Students Present | 7
Number of students Not Present | 1
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
We met to delegate tasks. To be honest, at the moment we are low on work. Several tasks are awaiting parts from mechanical or things that are on order.
Task Report
Milestone/Task | Due Date | Progress | Status
Drive System | 2018-02-14 | 12.5% | On Track
Assembly | 0 | 0% | On Track
E-Box | 0 | 0% | On Track
Wiring | 0 | 0% | On Track
Programming | 0 | 0% | On Track
Validation | 0 | 0% | On Track
Coltrol Systems | 0 | 0% | On Track
Navigation | 0 | 50% | On Track
Selecting/Procuring | 0 | 100% | On Track
Interfacing to sensors | 0 | 0% | On Track
Field Testing | 0 | 0% | On Track
Howe Hall Atrium | 0 | 0% | On Track
Richardson Ct. Asphault pile | 0 | 0% | On Track
Road Trip? | 0 | 0% | On Track
Arm System | 2018-04-23 | 16.25% | On Track
Arm System | 2018-04-23 | 16.25% | On Track
Components | 0 | 65% | On Track
Power Supply (20A dirty regulator) | 0 | 90% | On Track
Connectors | 0 | 40% | On Track
Power | 0 | 40% | On Track
Control | 0 | 40% | On Track
Assembly | 0 | 0% | On Track
E-Box | 0 | 0% | On Track
Arm | 0 | 0% | On Track
Controls | 0 | 0% | On Track
Base Rotation | 0 | 0% | On Track
Shoulder | 0 | 0% | On Track
Wrist | 0 | 0% | On Track
Claw | 0 | 0% | On Track
Testing | 0 | 0% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Drive System | James Talbert |  | 2018-02-14 |  | 12.5%
1.1 | Assembly |  |  |  |  | 0%
1.1.1 | E-Box |  |  |  |  | 0%
1.1.2 | Wiring |  |  |  |  | 0%
1.2 | Programming | Jefferson O'Brien |  |  |  | 0%
1.2.1 | Validation |  |  |  |  | 0%
1.2.2 | Coltrol Systems |  |  |  |  | 0%
1.3 | Navigation |  |  |  |  | 50%
1.3.1 | Selecting/Procuring |  |  |  |  | 100%
1.3.2 | Interfacing to sensors |  |  |  |  | 0%
1.4 | Field Testing |  |  |  |  | 0%
1.4.1 | Howe Hall Atrium |  |  |  |  | 0%
1.4.2 | Richardson Ct. Asphault pile |  |  |  |  | 0%
1.4.3 | Road Trip? |  |  |  |  | 0%
2 | Arm System | James Talbert |  | 2018-04-23 |  | 16.25%
2.1 | Components |  |  |  |  | 65%
2.1.1 | Power Supply (20A dirty regulator) | Jensen Mayes |  |  |  | 90%
2.1.2 | Connectors | James Talbert |  |  |  | 40%
2.1.2.1 | Power |  |  |  |  | 40%
2.1.2.2 | Control |  |  |  |  | 40%
2.2 | Assembly | Freshmen |  |  |  | 0%
2.2.1 | E-Box |  |  |  |  | 0%
2.2.2 | Arm |  |  |  |  | 0%
2.3 | Controls | Shivam Vashi |  |  |  | 0%
2.3.1 | Base Rotation |  |  |  |  | 0%
2.3.2 | Shoulder |  |  |  |  | 0%
2.3.3 | Elbow |  |  |  |  | 0%
2.3.4 | Wrist |  |  |  |  | 0%
2.3.5 | Claw |  |  |  |  | 0%
2.4 | Testing |  |  |  |  | 0%

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track