## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, you will also update your Atrack Excel file which contains the attendance records for this week. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Strategy Team
Team Leader Name | Gabe Gatmaitan
Week Number | 5
Attendance Records
Number of Students Present | 2
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
This week, the primary focus was on the power budget of MAVRIC. Consulting with matt and the rest of the teams we have found that the plan for the batteries should be changed, and fairly soon. Further testing of the rover and it's power usage should be fairly quick, and with that allow us to use cheaper, more readily avaliable, and smaller batteries.
Task Report
Milestone/Task | Due Date | Progress | Status
MAVRIC Control System | 2018-04-30 | 2.5% | On Track
Connect to Rover and control | 2018-02-15 | 5% | On Track
Be able to have high-uptime connectivity during testing | 2018-04-30 | 5% | On Track
MAVRIC Testing | 2018-03-20 | 0% | On Track
Test rover in regards to competition | 2018-03-15 | 0% | On Track
Build test rig to simulate competition tasks | 2018-03-15 | 0% | On Track
Consult Teams in regards to test and give feedback | 2018-03-20 | 10% | On Track
Competition Strategy | 2018-03-01 | 0% | On Track
Review Issues regarding last years competition | 2018-02-15 | 10% | On Track
Design testing around competition guideliens | 2018-03-01 | 5% | On Track
|  | 0% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | MAVRIC Control System |  | 2018-02-01 | 2018-04-30 |  | 2.5%
| Connect to Rover and control | Isaiah | 2018-02-01 | 2018-02-15 |  | 5% | bar: WEEK 3 M to WEEK 3 F
| Be able to have high-uptime connectivity during testing | Isaiah | 2018-02-01 | 2018-04-30 |  | 5% | bar: WEEK 4 M to WEEK 6 F
0% | bar: WEEK 7 M to WEEK 9 F
0%
0%
0%
0%
2 | MAVRIC Testing |  | 2018-02-01 | 2018-03-20
| Test rover in regards to competition | Gabe | 2018-02-15 | 2018-03-15 |  | 0%
| Build test rig to simulate competition tasks | Gabe | 2018-02-15 | 2018-03-15 |  | 0%
| Consult Teams in regards to test and give feedback | Gabe/Isaiah | 2018-03-01 | 2018-03-20 |  | 10%
0%
| Competition Strategy | Gabe | 2018-02-01 | 2018-03-01
| Review Issues regarding last years competition | Gabe | 2018-02-01 | 2018-02-15 |  | 10%
| Design testing around competition guideliens | Gabe/Isaiah | 2018-02-01 | 2018-03-01 |  | 5%
0%
0%
0%
0%
0%
0%
0%
0%

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track