## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, you will also update your Atrack Excel file which contains the attendance records for this week. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Electrical
Team Leader Name | James Talbert
Week Number | 9
Attendance Records
Number of Students Present | 8
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
We finished installing our bus bars and have tested our system's control of the wheels via the PWM HAT. Unfortunately we have learned that our battery charger does not work. It will power its fans off of the batteries, but recieves no power from the wall plug. This results in a discahrge of the batteries rather than a charge. This was a recent development, so I don't have a workaround yet. Diue to manufacturing delays, not all wheels are installed, and our testing capacity will be severely limited.
Task Report
Milestone/Task | Due Date | Progress | On Track
Drive System | 2018-03-18 | 72.92% | On Track
Assembly | 2018-02-23 | 85% | On Track
E-Box | 2018-02-23 | 90% | On Track
Wiring | 2018-02-23 | 80% | On Track
Programming | 2108-03-02 | 90% | On Track
Validation | 2108-03-02 | 90% | On Track
Control Systems | 2108-03-02 | 90% | On Track
Navigation | 2018-03-18 | 100% | On Track
Selecting/Procuring | 2018-03-18 | 100% | On Track
Interfacing to sensors | 2018-03-18 | 100% | On Track
Field Testing (iterative) | 2018-03-18 | 16.67% | High Risk
Howe Hall Atrium | 2018-03-18 | 50% | On Track
Richardson Ct. Asphault pile | 2018-03-18 | 0% | At Risk
Road Trip? | 2018-03-18 | 0% | Off Track
Everything Else | 2018-04-23 | 8.958% | High Risk
Science System | 2018-04-23 | 12.5% | On Track
Software | 2018-04-23 | 0% | On Track
Wiring | 2018-04-23 | 25% | On Track
E-Box | 2018-04-23 | 20% | On Track
SS Power/Control lines | 2018-04-23 | 30% | At Risk
Autonomous Driving | 2018-04-23 | 20% | On Track
Navigation Integration | 2018-04-23 | 20% | On Track
Control Software | 2018-04-23 | 20% | On Track
Arm | 2018-04-23 | 3.333% | High Risk
Wiring | 2018-04-23 | 10% | On Track
E-Box | 2018-04-23 | 0% | On Track
Arm Power/Control | 2018-04-23 | 20% | At Risk
Software | 2018-04-23 | 0% | At Risk
Validation | 2018-04-23 | 0% | At Risk
Integration Testing | 2018-06-01 | 0% | High Risk

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Drive System | James Talbert |  | 2018-03-18 |  | 72.92%
1.1 | Assembly |  | 2018-01-02 | 2018-02-23 |  | 85% | bar: WEEK 5 M to WEEK 9 F
1.1.1 | E-Box | Jensen Mayes | 2018-01-02 | 2018-02-23 |  | 90% | bar: WEEK 6 W to WEEK 9 F
1.1.2 | Wiring | Brady Anderson | 2018-01-02 | 2018-02-23 |  | 80% | bar: WEEK 6 W to WEEK 8 F
1.2 | Programming | Shivam Vashi | 2018-01-02 | 2108-03-02 |  | 90% | bar: WEEK 4 M to WEEK 9 F
1.2.1 | Validation | Jefferson O'Brien | 2018-01-02 | 2108-03-02 |  | 90% | bar: WEEK 7 M to WEEK 9 F
1.2.2 | Control Systems | Jefferson O'Brien | 2018-01-02 | 2108-03-02 |  | 90% | bar: WEEK 1 M to WEEK 2 F
1.3 | Navigation | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100% | bar: WEEK 5 M to WEEK 9 F
1.3.1 | Selecting/Procuring | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100%
1.3.2 | Interfacing to sensors | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100% | bar: WEEK 6 M to WEEK 8 F
1.4 | Field Testing (iterative) | [This is a group task] | 2108-03-02 | 2018-03-18 |  | 16.67%
1.4.1 | Howe Hall Atrium |  | 2108-03-02 | 2018-03-18 |  | 50%
1.4.2 | Richardson Ct. Asphault pile |  | 2108-03-02 | 2018-03-18 |  | 0%
1.4.3 | Road Trip? |  | 2108-03-02 | 2018-03-18 |  | 0%
2 | Everything Else | James Talbert |  | 2018-04-23 |  | 8.958%
2.1 | Science System |  | 2018-02-23 | 2018-04-23 |  | 12.5%
2.1.1 | Software | Shivam Vashi | 2018-03-18 | 2018-04-23 |  | 0%
2.1.2 | Wiring | Jensen Mayes | 2018-02-23 | 2018-04-23 |  | 25%
2.1.2.1 | E-Box | Alex Vande Loo | 2018-03-18 | 2018-04-23 |  | 20%
2.1.2.2 | SS Power/Control lines | Jensen Mayes | 2018-02-23 | 2018-04-23 |  | 30% | bar: WEEK 6 M to WEEK 9 F
2.2 | Autonomous Driving | Brady Anderson | 2018-02-23 | 2018-04-23 |  | 20%
2.2.1 | Navigation Integration | Morgan Foley, Jake Raymer | 2018-03-01 | 2018-04-23 |  | 20%
2.2.2 | Control Software | Brady Anderson, Jefferson O'Brien | 2018-02-23 | 2018-04-23 |  | 20%
2.3 | Arm |  | [Depends on Mech] | 2018-04-23 |  | 3.333%
2.3.1 | Wiring |  | [Depends on Mech] | 2018-04-23 |  | 10%
2.3.1.1 | E-Box |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.3.1.2 | Arm Power/Control |  | [Depends on Mech] | 2018-04-23 |  | 20%
2.3.4 | Software |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.3.5 | Validation |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.4 | Integration Testing |  |  | 2018-06-01 |  | 0%

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track