## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, you will also update your Atrack Excel file which contains the attendance records for this week. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Electrical
Team Leader Name | James Talbert
Week Number | 11
Attendance Records
Number of Students Present | 7
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
With charged batteries and the updated PWM drivers, we have tested the drive system to the limits of the mechanical hardware (there are some temporary 3D-printed) motor mounts that we have been told not to exectue turns with. We also learned that we were rejected from competition, so the team is adjusting some timelines to reduce the need for temporary solutions (e.g. the mechanical team is putting more time into arm design before manufacturing). Our priorities are autonomous navigation and the science system. Some aspects of the mechanical design of the science system are posing problems for power transmission to some of the motors. Also, as we will not have an arm to wire, develop controls for, or test, those systems are off track.
Task Report
Milestone/Task | Due Date | Progress | On Track
Drive System | 2018-03-18 | 83.33% | On Track
Assembly | 2018-02-23 | 100% | On Track
E-Box | 2018-02-23 | 100% | On Track
Wiring | 2018-02-23 | 100% | On Track
Programming | 2108-03-02 | 100% | On Track
Validation | 2108-03-02 | 100% | On Track
Control Systems | 2108-03-02 | 100% | On Track
Navigation | 2018-03-18 | 100% | On Track
Selecting/Procuring | 2018-03-18 | 100% | On Track
Interfacing to sensors | 2018-03-18 | 100% | On Track
Field Testing (iterative) | 2018-03-18 | 33.33% | Off Track
Howe Hall Atrium | 2018-03-18 | 100% | On Track
Richardson Ct. Asphault pile | 2018-03-18 | 0% | Off Track
Road Trip? | 2018-03-18 | 0% | Off Track
Everything Else | 2018-04-23 | 8.958% | High Risk
Science System | 2018-04-23 | 12.5% | On Track
Software | 2018-04-23 | 0% | On Track
Wiring | 2018-04-23 | 25% | At Risk
E-Box | 2018-04-23 | 20% | On Track
SS Power/Control lines | 2018-04-23 | 30% | At Risk
Autonomous Driving | 2018-04-23 | 20% | On Track
Navigation Integration | 2018-04-23 | 20% | On Track
Control Software | 2018-04-23 | 20% | On Track
Arm | 2018-04-23 | 3.333% | Off Track
Wiring | 2018-04-23 | 10% | Off Track
E-Box | 2018-04-23 | 0% | On Track
Arm Power/Control | 2018-04-23 | 20% | Off Track
Software | 2018-04-23 | 0% | Off Track
Validation | 2018-04-23 | 0% | Off Track
Integration Testing | 2018-06-01 | 0% | Off Track
s

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Drive System | James Talbert |  | 2018-03-18 |  | 83.33%
1.1 | Assembly |  | 2018-01-02 | 2018-02-23 |  | 100% | bar: WEEK 5 M to WEEK 11 F
1.1.1 | E-Box | Jensen Mayes | 2018-01-02 | 2018-02-23 |  | 100% | bar: WEEK 6 W to WEEK 11 F
1.1.2 | Wiring | Brady Anderson | 2018-01-02 | 2018-02-23 |  | 100% | bar: WEEK 6 W to WEEK 8 F; WEEK 10 M to WEEK 11 F
1.2 | Programming | Shivam Vashi | 2018-01-02 | 2108-03-02 |  | 100% | bar: WEEK 4 M to WEEK 11 F
1.2.1 | Validation | Jefferson O'Brien | 2018-01-02 | 2108-03-02 |  | 100% | bar: WEEK 7 M to WEEK 9 F; WEEK 10 F to WEEK 11 F
1.2.2 | Control Systems | Jefferson O'Brien | 2018-01-02 | 2108-03-02 |  | 100% | bar: WEEK 1 M to WEEK 2 F; WEEK 10 F to WEEK 11 F
1.3 | Navigation | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100% | bar: WEEK 5 M to WEEK 9 F
1.3.1 | Selecting/Procuring | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100%
1.3.2 | Interfacing to sensors | Morgan Foley | 2018-01-02 | 2018-03-18 |  | 100% | bar: WEEK 6 M to WEEK 8 F
1.4 | Field Testing (iterative) | [This is a group task] | 2108-03-02 | 2018-03-18 |  | 33.33%
1.4.1 | Howe Hall Atrium |  | 2108-03-02 | 2018-03-18 |  | 100%
1.4.2 | Richardson Ct. Asphault pile |  | 2108-03-02 | 2018-03-18 |  | 0%
1.4.3 | Road Trip? |  | 2108-03-02 | 2018-03-18 |  | 0%
2 | Everything Else | James Talbert |  | 2018-04-23 |  | 8.958%
2.1 | Science System |  | 2018-02-23 | 2018-04-23 |  | 12.5%
2.1.1 | Software | Shivam Vashi | 2018-03-18 | 2018-04-23 |  | 0%
2.1.2 | Wiring | Jensen Mayes | 2018-02-23 | 2018-04-23 |  | 25% | bar: WEEK 6 M to WEEK 11 F
2.1.2.1 | E-Box | Alex Vande Loo | 2018-03-18 | 2018-04-23 |  | 20%
2.1.2.2 | SS Power/Control lines | Jensen Mayes | 2018-02-23 | 2018-04-23 |  | 30% | bar: WEEK 6 M to WEEK 11 F
2.2 | Autonomous Driving | Brady Anderson | 2018-02-23 | 2018-04-23 |  | 20% | bar: WEEK 8 M to WEEK 11 F
2.2.1 | Navigation Integration | Morgan Foley, Jake Raymer | 2018-03-01 | 2018-04-23 |  | 20% | bar: WEEK 7 M to WEEK 11 F
2.2.2 | Control Software | Brady Anderson, Jefferson O'Brien | 2018-02-23 | 2018-04-23 |  | 20% | bar: WEEK 8 M to WEEK 11 F
2.3 | Arm |  | [Depends on Mech] | 2018-04-23 |  | 3.333%
2.3.1 | Wiring |  | [Depends on Mech] | 2018-04-23 |  | 10%
2.3.1.1 | E-Box |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.3.1.2 | Arm Power/Control |  | [Depends on Mech] | 2018-04-23 |  | 20%
2.3.4 | Software |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.3.5 | Validation |  | [Depends on Mech] | 2018-04-23 |  | 0%
2.4 | Integration Testing |  |  | 2018-06-01 |  | 0%

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track