## Instructions
Individual team reports are due no later than 12:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Team Leader and Project Leader. To use this report, update your tasks and the progress on each task. You must also give us some comments on what you worked on and this must be at least two complete sentences. When done, upload this Excel file to corresponding assignment in Canvas and email it to your Team Leader and Project Leader. If you have any questions please contact Matthew Nelson (mnelson@iastate.edu) or Christine Nelson (cnnelson@iastate.edu)

## Weekly Task Report
M:2:I Individual Task Report
Weekly individual task reports are due no later than 12:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Electrical Team
Your Name | Brady Anderson
Week Number | 5
Individual Status Report
My tasks are currently: | On Track
Please put any comments below on your status with your tasks.
Successfully tested the Raspberry Pi PWM hat and associated Adafruit library. The hat allows a single Raspberry Pi to control 16 PWM devices instead of just 1 or 2, and will be used to send signals to our Talon SRX motor controllers. Also researched possible sources of high-current busbar for power distribution.
Task Report
Task | Due Date | Progress | Status
Test Raspberry Pi PWM hat | 2018-02-10 | 100% | On Track
Research busbar | 2018-02-03 | 100% | On Track
On Track
On Track
On Track
On Track
On Track
On Track
On Track
Note on B4: Matthew Nelson: Enter your Project Name here. This must be filled out.
Note on B5: Matthew Nelson: Enter your team name here. This must be filled out.
Note on B6: Matthew Nelson: Enter your name here. This must be filled out or you will not get any credit for your report.
Note on B7: Matthew Nelson: Enter the week number for this report.
Note on B9: Matthew Nelson: Use the drop down menu to select if you are on track, at risk, or off track. You do not lose points for being off track and expect that you will be honest with us in reporting this.
Note on A20: Matthew Nelson: You must place the tasks you are working on here.
Note on B20: Matthew Nelson: You must put the due dates for your tasks here
Note on C20: Matthew Nelson: Enter a progress from 0% to 100%

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track